## Critical Path Example
CRITICAL PATH
|  | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27
Activity |  | 2024-07-18: Pre; 2024-08-01: Brand Awareness; 2024-09-05: Warm Up; 2024-10-03: Lead Acquisition; 2024-10-31: Pre-Sale; 2025-01-02: Launch
DIGITAL BRAND LAUNCH | Owner | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27
Website Refresh
Homepage takeover
Registration forms in place
E-newsletter to databases
Social media content planner
App updated
WARM UP - FACILITY FOCUSSED | Owner | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27
Campaign planner draft
Campaign planner and copy signed off
Search PPC adverts
Social media adverts
Local / community engagement
Confirm pre-sale offers and incentives
LEAD ACQUISITION - PRODUCT FOCUSSED | Owner | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27
Campaign planner sent
Campaign planner and copy signed off
Lead capture forms in place
Google PPC adverts (CONVERSIONS - LEADS)
Meta paid adverts (Facebook & Instagram - General Audience - LEADS)
e-Newsletter to databases
PRE-SALE | Owner | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27
Any pre-sale offers or bookings added to LMS / programmed in
Campaign planner and copy signed off
Offers / pre-sale information added to website
Offers / pre-sale information sent out to VIP mailing list via email/SMS
Search PPC adverts
Social media adverts
VIP open day / stakeholder ribbon cutting event
Photoshoot / videoshoot after handover is completed or during open day
Press release
Update of assets to include new photography/videography
LAUNCH | Owner | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27
Website updated
SMS Campaign
e-Newsletter sent to databases
Search PPC adverts
Social media adverts
Snapchat adverts
YouTube Adverts
TikTok Adverts

## Activity Template
INSERT ACTIVITY DESCRIPTION
Campaign or Activity | Dates | Objective | Budget | Description | Call-To-Action / Hook | Target Groups | Marketing Channels